## Module Matrix
# | Module Name | Layer | Phase | Priority | Revenue Impact | Complexity | Est Hours | Status | Existing RaniOS Coverage | Key APIs / Integrations | Primary Airtable Tables | Owner | Dependencies | Notes
1 | Lead Router | Sales OS | 1 | Very High | Direct Revenue | Medium | 20 | Exists-Partial | WF1/WF2 intake processing + lead funnel. Missing: routing rules, provider assignment, priority scoring | Airtable, n8n, Mangomint | Clients, Appointments, Alerts | Dev | None | Highest ROI - connects Growth to Sales
2 | Discovery Call Closer | Sales OS | 1 | Very High | Direct Revenue | High | 30 | Exists-Partial | Consult copilot engine with objection handlers + closing strategies. Missing: call recording, outcome tracking, script analytics | Airtable, Vapi | Appointments, Clients, Transactions | CEO | Lead Router | Core revenue driver
3 | Treatment Plan Generator | Sales OS | 1 | Very High | Direct Revenue | Low | 5 | Exists-Complete | TreatmentPlanClient.tsx (1315 lines) - 3-tier pricing, AI intake, financing calc, roadmap. Fully built. | Airtable, Resend, Twilio | Client Intakes, Intake Intelligence | Dev | None | Already built and working
4 | Client Onboarding | Client Experience OS | 1 | Very High | Revenue Protection | Medium | 25 | Exists-Partial | Pre-consult templates (3-step), post-treatment (5-step), WF4 prep. Missing: unified flow, consent tracking | Mangomint, Airtable, Jotform, Resend | Appointments, Clients, Messages Log | Operations | Treatment Plan Generator | Reduces no-shows and anxiety
5 | Reactivation Machine | Client Experience OS | 1 | Very High | Revenue Recovery | Medium | 15 | Exists-Partial | Reactivation templates (3-tier), WF8, churn engine, at-risk list. Missing: multi-channel, personalized offers | Airtable, n8n, Resend, Twilio | Clients, Transactions, Messages Log | Marketing | Churn Engine | Wake up dormant revenue from 2437 clients
6 | Review & Referral Machine | Client Experience OS | 1 | Very High | Trust Building | Medium | 20 | Exists-Partial | W13 Review Commander, review table, AI responses. Missing: referral program, ambassador tracking, negative interception | Google, Airtable, Resend | Reviews, Clients, Messages Log | Marketing | Client Onboarding | Compounds growth via social proof
7 | IG Client Machine | Growth OS | 2 | High | Direct Revenue | High | 40 | Exists-Partial | Social auto-post generates calendar + captions. Missing: DM automation, story CTA tracking, lead scoring, booking handoff | Instagram/Meta, Airtable, n8n | Clients, Campaigns | Marketing | None | Instagram is #1 medspa channel
8 | Meta Ads Machine | Growth OS | 2 | High | Direct Revenue | Medium | 15 | Exists-Partial | Real Meta API integration, campaign grading, budget optimization, fatigue detection. Missing: auto bid, dynamic audiences | Meta Ads API, Airtable | Transactions, Clients | Marketing | None | Strongest external integration
9 | FB Group Machine | Growth OS | 2 | Medium-High | Direct Revenue | Medium | 25 | Not Started | Nothing exists | Facebook, Airtable, n8n | Clients, Campaigns | Marketing | None | Local community mining
10 | Cold Call Script Machine | Growth OS | 2 | High | Direct Revenue | Medium | 20 | Exists-Partial | Consult copilot objection handlers reusable. Vapi call flows. Missing: script library UI, performance tracking | Vapi, Airtable | Clients, Appointments | CEO | Vapi Phone Agent | Leverage existing copilot intelligence
11 | Offer Engine | Sales OS | 2 | High | Direct Revenue | High | 30 | Exists-Partial | Dynamic pricing (6 strategies), seasonal multipliers, packages. Missing: offer selection, urgency, channel matching | Airtable, n8n | Transactions, Clients, Appointments | CEO | Lead Router | Right offer right time
12 | Sales Objection Intelligence | Sales OS | 2 | High | Direct Revenue | Medium | 20 | Exists-Partial | 6 objection handlers (feel-felt-found, reframe, etc). Missing: tagging from real calls, frequency analysis, A/B testing | Airtable | Appointments, Clients | CEO | Discovery Call Closer | Learn what stops buying
13 | Case Study Builder | Client Experience OS | 3 | High | Trust Building | Medium | 20 | Not Started | B/A photo consent in Jotform. Missing: template generator, proof library, social proof snippets, ad creative gen | Airtable, Canva | Clients, Appointments, Reviews | Marketing | Review & Referral | Results become sales assets
14 | Content Flywheel Engine | Growth OS | 3 | Medium-High | Trust Building | High | 30 | Exists-Partial | Social auto-post generates weekly calendar. Missing: multi-format repurposing, hook library, approval queue | Airtable, Meta | Reviews, Clients | Marketing | Case Study Builder | Multiply content output
15 | Local SEO / GEO Machine | Growth OS | 3 | High | Direct Revenue | High | 35 | Not Started | IndexNow API route exists. Missing: city/service pages, GBP calendar, rank monitoring, FAQ generation | Google Business Profile, Airtable | Reviews, Competitors | Marketing | None | Capture search intent
16 | Reputation Monitor | Client Experience OS | 3 | Medium | Trust Building | Medium | 15 | Exists-Partial | W13 Review Commander + Competitor Intel table. Missing: sentiment trending, competitor mining, topic clustering | Google, Airtable | Reviews, Competitor Intelligence | Marketing | Review & Referral | Watch market perception
17 | Provider Performance Engine | Operator OS | 4 | High | Efficiency | Medium | 15 | Exists-Partial | Provider routes + WF10. Missing: close rate, rebook rate, coaching prompts, incentives, benchmarks | Airtable | Appointments, Transactions, Reviews | Operations | None | Make staff measurable
18 | Financing Conversion Machine | Sales OS | 4 | High | Direct Revenue | Medium | 20 | Exists-Partial | Cherry refs in plan page + WF6. Missing: application tracking, decline recovery, approval dashboard | Cherry/Stripe, Airtable, n8n | Transactions, Clients | CEO | Treatment Plan Generator | Close rate on $2K+ cases
19 | Inventory Control Machine | Operator OS | 4 | High | Revenue Protection | Medium | 10 | Exists-Partial | Engine is production-grade. Route queries Airtable. Missing: barcode scanning, vendor ordering, auto-tracking | Airtable | Appointments, Alerts | Operations | None | Stop inventory leaks
20 | LinkedIn Client Machine | Growth OS | 4 | Medium | Direct Revenue | High | 35 | Not Started | Nothing exists | LinkedIn, Airtable | Clients, Campaigns | CEO | None | Higher-income + B2B authority
21 | Auto Agent Builder | Agent OS | 4 | High | Efficiency | Very High | 50 | Not Started | RAG KB + Vapi + AI chat foundation. Missing: agent templates, permissions, triggers, deployment framework | OpenAI/Claude, Airtable, n8n | Agents, Prompts, Workflows, Logs | Dev | All Phase 1-3 | Platform play
22 | Lead Follow-Up Agent | Agent OS | 4 | High | Direct Revenue | Medium | 10 | Exists-Partial | WF2 + WF2b follow-up ladder. Missing: multi-channel, personalization, give-up logic | n8n, Airtable, Resend, Twilio | Clients, Messages Log | Dev | Auto Agent Builder | Follow up until booked
23 | No-Show Recovery Agent | Agent OS | 4 | High | Revenue Recovery | Low | 8 | Exists-Partial | No-show prediction engine. Missing: auto recovery (SMS 15min, call 1hr, reschedule 24h) | n8n, Airtable, Twilio | Appointments, Clients | Dev | No-Show Predictor | Recover missed appointments
24 | Reactivation Agent | Agent OS | 4 | High | Revenue Recovery | Low | 8 | Exists-Partial | WF8 + templates. Missing: AI-personalized messaging, multi-touch, response handling | n8n, Airtable, Resend, Twilio | Clients, Messages Log | Dev | Reactivation Machine | Auto dormant recovery
25 | Consultation Prep Agent | Agent OS | 4 | Medium-High | Efficiency | Low | 5 | Exists-Complete | WF4 daily 6AM + consult copilot + pre-consult templates. | n8n, Airtable | Appointments, Client Intakes | Dev | None | Already mostly built
26 | Review Request Agent | Agent OS | 4 | Medium-High | Trust Building | Low | 5 | Exists-Partial | W13 Review Commander. Missing: timing optimization, satisfaction check, platform routing | n8n, Airtable | Reviews, Appointments | Dev | Review & Referral | Right timing for requests
27 | Content Repurposing Agent | Agent OS | 4 | Medium | Trust Building | Medium | 15 | Not Started | Social engine exists but no repurposing. Missing: input-to-multi-format pipeline | Airtable, Claude API | Reviews, Clients | Dev | Content Flywheel | Turn 1 proof into 5 assets
28 | Daily KPI Briefing Agent | Agent OS | 4 | Medium-High | Efficiency | Low | 8 | Exists-Partial | Weekly revenue report task. Missing: daily morning briefing, actionable steps, target comparison | n8n, Airtable, Resend | KPI Snapshots, Transactions | Dev | KPI Command Center | CEO morning briefing
29 | SOP Coach Agent | Agent OS | 4 | Medium | Efficiency | High | 25 | Not Started | RAG KB has 12 docs. Missing: SOP library, interactive training, compliance checking, staff quizzes | Claude API, Airtable | Agents, Prompts | Dev | Auto Agent Builder + RAG | Help staff follow process
30 | KPI Command Center | Operator OS | Existing | Very High | Efficiency | N/A | 0 | Exists-Complete | Real-time KPIs, gamification, alerts. 6 parallel Airtable queries. Fully functional. | Airtable | All tables | Operations | None | Core dashboard - WORKING
31 | P&L Engine | Operator OS | Existing | High | Revenue Protection | N/A | 0 | Exists-Complete | Expense categorization, margins, health scoring, projections. Post-fix: uniqueClients corrected. | Airtable | Transactions, Memberships | CEO | None | Financial visibility - WORKING
32 | Schedule Optimizer | Operator OS | Existing | High | Efficiency | N/A | 0 | Exists-Complete | Gap detection, conflicts, provider balance, revenue opportunities. Real data. | Airtable | Appointments | Operations | None | Schedule intelligence - WORKING
33 | No-Show Predictor | Operator OS | Existing | High | Revenue Protection | N/A | 0 | Exists-Complete | 6-factor prediction. Post-fix: real client history passed. | Airtable | Appointments, Clients | Operations | None | Post-fix: FULLY FUNCTIONAL
34 | Churn Engine | Operator OS | Existing | High | Revenue Recovery | N/A | 0 | Exists-Complete | 5-factor RFM. Post-fix: real engagement score. | Airtable | Clients, Appointments, Transactions, Memberships, Messages Log | Operations | None | Post-fix: FULLY FUNCTIONAL

## Airtable Tables
Table Name | Exists? | Used by Modules | Priority | Notes
Clients | YES - Live | ALL modules | Existing | CRM core - 2437 records
Client Intakes | YES - Live | Treatment Plan Generator, Lead Router | Existing | Typeform submissions + AI analysis
Intake Intelligence | YES - Live | Treatment Plan Generator | Existing | AI-processed intake data
Appointments | YES - Live | Schedule Optimizer, No-Show, Provider Perf, Onboarding | Existing | Schedule, utilization, consults
Packages | YES - Live | Offer Engine, Treatment Plan Generator | Existing | Treatment packages sold
Memberships | YES - Live | Reactivation, Churn, P&L, Financing | Existing | Monthly membership tracking
Transactions | YES - Live | KPI, P&L, Revenue, Provider Perf, Financing | Existing | Revenue, payments, financing
Messages Log | YES - Live | Churn, Onboarding, Reactivation, Follow-Up Agent | Existing | SMS/email audit trail
Reviews | YES - Live | Review & Referral, Reputation Monitor, Case Study | Existing | Google review tracking + AI responses
KPI Snapshots | YES - Live | KPI Command Center, Daily Briefing Agent | Existing | Daily/weekly metric snapshots
Alerts | YES - Live | KPI, Inventory, Entry forms | Existing | System alerts + thresholds
Competitor Intelligence | YES - Live | Reputation Monitor, Dynamic Pricing | Existing | Competitor monitoring
Leads | NO | Lead Router, IG Machine, FB Group, Cold Call, SEO | High | Dedicated lead table separate from Clients
Lead Sources | NO | Lead Router, Meta Ads, IG Machine, SEO | High | Attribution tracking
Campaigns | NO | Meta Ads, IG Machine, FB Group, Offer Engine, Content | High | Campaign management across channels
Content Calendar | NO | IG Machine, Content Flywheel, Social Auto-Post | Medium-High | Multi-channel content planning
Conversations | NO | IG Machine, FB Group, LinkedIn, Cold Call | Medium | DM/message thread tracking
Consults | NO | Discovery Call Closer, Sales Objection Intel | High | Consult outcome tracking (separate from Appointments)
Treatment Plans | NO | Treatment Plan Generator, Case Study Builder | Medium | Persistent plan records
Quotes | NO | Discovery Call Closer, Offer Engine | Medium | Pricing quotes sent to clients
Financing | NO | Financing Conversion Machine, Treatment Plan Gen | High | Application status, approval tracking
Objections | NO | Sales Objection Intel, Discovery Call Closer | Medium | Objection tagging + scripts
Offers | NO | Offer Engine, Reactivation, Lead Router | High | Offer catalog with redemption tracking
Referrals | NO | Review & Referral Machine | Medium-High | Referral source + reward attribution
Case Studies | NO | Case Study Builder, Content Flywheel | Medium | Before/after proof assets
Assets | NO | Case Study Builder, Content Flywheel, IG Machine | Medium | Creative asset library
Providers | NO | Provider Performance Engine, Schedule Optimizer | Medium | Provider profiles (vs hardcoded)
Routing Rules | NO | Lead Router | Medium | Lead assignment logic
Tasks | NO | Lead Router, Onboarding, Auto Agent Builder | Medium | Staff task assignments
Workflows | NO | Auto Agent Builder | Low | Agent workflow definitions
Agents | NO | Auto Agent Builder | Low | Agent configurations
Prompts | NO | Auto Agent Builder, SOP Coach | Low | Prompt library
Logs | NO | Auto Agent Builder, all agents | Low | Agent execution logs
Reputation Events | NO | Reputation Monitor | Low | Sentiment tracking events
SEO Pages | NO | Local SEO / GEO Machine | Medium | City/service page tracking
Local Keywords | NO | Local SEO / GEO Machine | Medium | Rank tracking keywords
Rank Tracking | NO | Local SEO / GEO Machine | Medium | SERP position history
GBP Posts | NO | Local SEO / GEO Machine | Medium | Google Business Profile posts
Ambassadors | NO | Review & Referral Machine | Low | VIP referral partners
Service Economics | NO | Meta Ads, Offer Engine, Dynamic Pricing | Medium | Per-service unit economics

## Build Order
Sprint # | Week | Modules | Hours | Revenue Impact | Cumulative Score
1 | Week 1-2 | Lead Router + Treatment Plan Generator (polish) | 20+5=25 | Leads route to right workflow. Plans already convert. | 73 → 78
2 | Week 3-4 | Discovery Call Closer + Client Onboarding | 30+25=55 (30 this sprint) | Consults close at higher rate. Clients feel handled. | 78 → 82
3 | Week 5 | Client Onboarding (complete) + Reactivation Machine | 25+15=40 (25 this sprint) | Dormant clients re-engaged. No-shows reduced. | 82 → 85
4 | Week 6 | Review & Referral Machine + Offer Engine (start) | 20+10=30 | Reviews compound. Right offers at right time. | 85 → 87
5 | Week 7 | Offer Engine (complete) + Meta Ads Machine (enhance) | 20+15=35 (20 this sprint) | Ad spend optimized. Offers match lead intent. | 87 → 89
6 | Week 8 | IG Client Machine + Cold Call Script Machine (start) | 40 (20 this sprint) | Instagram leads flow into Lead Router. | 89 → 90
7 | Week 9 | IG Machine (complete) + Cold Call Scripts + Sales Objection Intel | 20+20+10=50 (20 this sprint) | Outbound calls convert. Objections tracked. | 90 → 91
8 | Week 10 | Case Study Builder + Content Flywheel Engine (start) | 20+10=30 (20 this sprint) | Results become multi-channel trust assets. | 91 → 92
9 | Week 11 | Local SEO/GEO Machine + Provider Performance Engine | 35+15=50 (20 this sprint) | Search intent captured. Staff measured. | 92 → 93
10 | Week 12 | Financing Conversion + Daily Briefing Agent + Review Request Agent | 20+8+5=33 (20 this sprint) | Close $2K+ cases. CEO gets daily intel. | 93 → 94
Backlog | Week 13+ | FB Group, LinkedIn, Auto Agent Builder, sub-agents, SOP Coach, Inventory enhancements, Reputation Monitor | ~200 remaining | Platform-level capabilities. Multi-tenant prep. | 94 → 97

## Revenue Impact
Module | Monthly Impact (Low) | Monthly Impact (High) | Time to Revenue | ROI Rank
Lead Router | 3000 | 8000 | 2 weeks | 1
Discovery Call Closer | 5000 | 15000 | 3 weeks | 2
Treatment Plan Generator | 2000 | 5000 | Already live | 3
Client Onboarding | 2000 | 6000 | 4 weeks | 5
Reactivation Machine | 8000 | 25000 | 2 weeks | 4
Review & Referral Machine | 3000 | 10000 | 6 weeks | 6
IG Client Machine | 5000 | 20000 | 6 weeks | 7
Meta Ads Machine (enhanced) | 3000 | 12000 | 2 weeks | 8
FB Group Machine | 1000 | 5000 | 8 weeks | 14
Cold Call Script Machine | 3000 | 10000 | 3 weeks | 9
Offer Engine | 4000 | 15000 | 4 weeks | 10
Sales Objection Intelligence | 2000 | 8000 | 6 weeks | 12
Case Study Builder | 1000 | 5000 | 8 weeks | 15
Content Flywheel Engine | 1000 | 4000 | 8 weeks | 18
Local SEO / GEO Machine | 3000 | 12000 | 12 weeks | 11
Reputation Monitor | 500 | 2000 | 8 weeks | 20
Provider Performance Engine | 2000 | 8000 | 4 weeks | 13
Financing Conversion Machine | 5000 | 20000 | 3 weeks | 5
Inventory Control Machine | 500 | 2000 | 6 weeks | 19
LinkedIn Client Machine | 1000 | 5000 | 12 weeks | 17
Auto Agent Builder | 2000 | 10000 | 16 weeks | 16
Lead Follow-Up Agent | 3000 | 10000 | 2 weeks | 8
No-Show Recovery Agent | 2000 | 6000 | 1 week | 10
Reactivation Agent | 4000 | 15000 | 2 weeks | 6
Consultation Prep Agent | 1000 | 3000 | Already live | 21
Review Request Agent | 1000 | 4000 | 2 weeks | 16
Content Repurposing Agent | 500 | 2000 | 6 weeks | 22
Daily KPI Briefing Agent | 0 | 0 | 1 week | 23
SOP Coach Agent | 500 | 2000 | 12 weeks | 24
TOTAL POTENTIAL |  |  | If all modules deployed